## General Info
Order | Order Type | Bas. start date | Description | Description | Functional loc. | System status | User status | Entered by | Changed by | WBS element | WBS ord. header | Actual release | Basic fin. date
402022836 | ZPM2 | 2015-06-15 | GAM-ALARM 2106 T-MEASUREMENT FAILURE | G97 / 78 / 3 - Patton | WF-US-0PA-1121-Y2-A-003 | CLSD PCNF NMAT SETC | COMP | USUARIOJOBS | IDUCAY01 |  |  | 2015-06-15 | 2015-06-15
402024751 | ZPM2 | 2015-06-16 | REPLACED THE DECK SUPPORT RODS | G97 / 90 / 17 - Patton | WF-US-0PA-1121-Y2-A-009 | CLSD PCNF GMPS NMAT SETC | COMP | USUARIOJOBS | IDUCAY01 |  |  | 2015-06-16 | 2015-06-16
402024772 | ZPM2 | 2015-06-16 | REPLACED THE DECK SUPPORT ROD | G97 / 90 / 5 - Patton | WF-US-0PA-1121-Y2-A-005 | CLSD PCNF GMPS NMAT SETC | COMP | USUARIOJOBS | IDUCAY01 |  |  | 2015-06-16 | 2015-06-16
402027021 | ZPM2 | 2015-06-18 | AUTOLUBBER DM | G97 / 90 / 17 - Patton | WF-US-0PA-1121-Y2-A-009 | REL PCNF GMPS NMAT SETC | ACCE | USUARIOJOBS | OSB_RFC01 |  |  | 2015-06-18 | 2015-06-18

## Hours (Labor)
Order | Turbine Number | Start Date | Sta. Hour | End Date | End Hour | Work type | Pers.No. | Personnel Name | Subc | Name | OT Description | Type | User Statu | Windfarm c | Windf.Des. | Functional Location | PlPl | Stop Cause | Stop Cause | Stop. work | Stopped Wo | Windf. | WO Description | Work | Work Code | Work description | Work Hours | Total Hour | Postg date
402022836 | G97 / 78 / 3 - Patton | 2015-06-15 | 06:50:00 | 2015-06-15 | 07:15:00 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | 500504 | Gamesa Wind USA | GAM-ALARM 2106 T-MEASUREMENT FAILURE | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-003 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | 2000541: LOCAL RESET | 0.42 | 25 | 2015-06-15
402024751 | G97 / 90 / 17 - Patton | 2015-06-16 | 08:25:00 | 2015-06-16 | 11:10:00 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | 500504 | Gamesa Wind USA | REPLACED THE DECK SUPPORT RODS | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-009 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 2.75 | 165 | 2015-06-16
402024751 | G97 / 90 / 17 - Patton | 2015-06-16 | 08:25:00 | 2015-06-16 | 11:10:00 | Op regular hours | 2000541 | Robert Anthony Cook | 500504 | Gamesa Wind USA | REPLACED THE DECK SUPPORT RODS | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-009 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 2.75 | 165 | 2015-06-16
402024772 | G97 / 90 / 5 - Patton | 2015-06-16 | 12:00:00 | 2015-06-16 | 12:45:00 | Op regular hours | 2000541 | Robert Anthony Cook | 500504 | Gamesa Wind USA | REPLACED THE DECK SUPPORT ROD | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-005 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 0.75 | 45 | 2015-06-16
402024772 | G97 / 90 / 5 - Patton | 2015-06-16 | 12:00:00 | 2015-06-16 | 12:45:00 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | 500504 | Gamesa Wind USA | REPLACED THE DECK SUPPORT ROD | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-005 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 0.75 | 45 | 2015-06-16
402027021 | G97 / 90 / 17 - Patton | 2015-06-18 | 10:00:00 | 2015-06-18 | 10:45:00 | Op regular hours | 2000507 | Nathan Paul Palko | 500504 | Gamesa Wind USA | AUTOLUBBER DM | ZPM2 | Accepted | 1121 | Patton | WF-US-0PA-1121-Y2-A-009 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | 2000541: AUTOLUBBER DM | 0.75 | 45 | 2015-06-18

## Stop Times
Order | Order Type | Plant | FunctLocDescrip. | Descriptn | WO Description | Windfarm | Start Date | Time | End date | Stop time | Total Stop | Functional Location | External c | Descrip. o | Ext. Cause | Internal c | Descrip. o | Int. Cause | UserStatus | Line Hours | Employee | Production | Wind T. Av | WindT. hou | Disconnec. | Con. Hour | Name | System Status | Remarks
402022836 | ZPM2 | 1320 | G97 / 78 / 3 - Patton | Patton | GAM-ALARM 2106 T-MEASUREMENT FAILURE | WF-US-0PA-1121 | 2015-06-15 | 03:30:00 | 2015-06-15 | 07:05:00 | 3:35:00 | WF-US-0PA-1121-Y2-A-003 | 0 |  |  | 0 |  |  | COMP | 21971 | 2000541 | 20171558.00 KWH |  | 21701 | 00:00:00 | 00:00:00 | Robert Anthony Cook | CLSD PCNF NMAT SETC | 2000541: LOCAL RESET
402024751 | ZPM2 | 1320 | G97 / 90 / 17 - Patton | Patton | REPLACED THE DECK SUPPORT RODS | WF-US-0PA-1121 | 2015-06-16 | 08:55:00 | 2015-06-16 | 11:10:00 | 2:15:00 | WF-US-0PA-1121-Y2-A-009 | 0 |  |  | 0 |  |  | COMP | 21558 | 2000541 | 17642588.00 KWH |  | 21235 | 00:00:00 | 00:00:00 | Robert Anthony Cook | CLSD PCNF GMPS NMAT SETC
402024772 | ZPM2 | 1320 | G97 / 90 / 5 - Patton | Patton | REPLACED THE DECK SUPPORT ROD | WF-US-0PA-1121 | 2015-06-16 | 12:00:00 | 2015-06-16 | 12:45:00 | 0:45:00 | WF-US-0PA-1121-Y2-A-005 | 0 |  |  | 0 |  |  | COMP | 21803 | 2000541 | 18695024.00 KWH |  | 21422 | 00:00:00 | 00:00:00 | Robert Anthony Cook | CLSD PCNF GMPS NMAT SETC
402027021 | ZPM2 | 1320 | G97 / 90 / 17 - Patton | Patton | AUTOLUBBER DM | WF-US-0PA-1121 | 2015-06-18 | 10:00:00 | 2015-06-18 | 10:45:00 | 0:45:00 | WF-US-0PA-1121-Y2-A-009 | 0 |  |  | 0 |  |  | ACCE | 21528 | 2000541 | 17615674.00 KWH |  | 21205 | 00:00:00 | 00:00:00 | Robert Anthony Cook | REL PCNF GMPS NMAT SETC | 2000541: AUTOLUBBER DM

## Consumption
Order | Plnt | SLoc | Material | Material Description | MvT | Quantity in UnE | Amount in LC | Pstng Date
402027021 | 1320 | 1121 | 181921 | Rubbish Bag 85 x 105 (Roll of 20 units) | 965 | -1 | -0.42 | 2015-06-18
402027021 | 1320 | 1121 | 8045300078 | CABLE H07V-K 450-750V 1X1,5MM2 CU BLUE | 965 | -4 | -1.08 | 2015-06-18
402027021 | 1320 | 1121 | CAX0089 | AUXILIARY CONTACT CA5 10 1NO | 965 | -1 | -2.5 | 2015-06-18
402024772 | 1320 | 1121 | GP099847 | BOLTS PLATFORMS FLANGE | 965 | -1 | -96.2 | 2015-06-17
402024751 | 1320 | 1121 | GP099847 | BOLTS PLATFORMS FLANGE | 965 | -1 | -96.2 | 2015-06-16
402027021 | 1320 | 1121 | P390056 | TERMINAL 1.5 mm2 | 965 | -6 | -0.1 | 2015-06-18
402027021 | 1320 | 1121 | P392932 | LABEL FOR SINGLE-LINE CABLE | 965 | -6 | -1.44 | 2015-06-18