## WIR
|  | Notification-No.: |  |  |  | SAP-Job-No.: |  |  |  | Engineer Name/Personnel-No.:
|  | 874105 |  |  |  | 60077492 |  |  |  | Jesse Jones - 20334
|  | Operation Hours: |  |  |  | MWh: |  |  |  | Joel Keeler - 20562
Work and Installation Report Maintenance Protocol RENA Use Only - Valid from 12JUN2013 |  | 9303 |  |  |  | 6843
|  | Location/Serial-No.: |  |  |  | WEC-Type:
|  | Twin Ridges |  | 57-91942 |  | MM92 100M NCV
Work Report/Description of Work | [7 empty] | Date (MM-DD-YY): |  | 2013-11-07
[8 empty] | Time |  | Working Hours | Activity for Work Order | SAP Code (OIC Only) | Initials if Working Hours Differ
Third day of the 1st annual maintenance per Repower service manual T-2.1-GP.WA.02-A (F)-EN. yearly maintenance safety equipment annual maintenance service agreement testing equipment like chain, fire extinguisher, running, climbing aid, first aid kit, crane and/ or lift inspection The maintenance is now complete on this turbine. | [7 empty] | From | Until
[8 empty] | 7:30 | 9:00 | 1:30 | Job Prep | AVPRE
[8 empty] | 9:00 | 9:10 | 0:10 | Drive Time | FFBRE
[8 empty] | 9:10 | 17:30 | 8:20 | Work on Turbine | MOSRE
Turbine Offline in REguard (MM-DD-YY / HH:MM): |  | 2013-11-07 | 9:11 | Time Offline: |  | Work Finished: |  |  |  | WEC Ready to Start:
Turbine Online in REguard (MM-DD-YY / HH:MM): |  | 2013-11-07 | 17:04 | 0.32847
Material | [10 empty] | Type of Work Performed
No. | Description of Material | New | Refurb (A) | Defect (D) | SAP-No. | Amount | Units | Storage | Serial Number
1 | Grease absorber PVC-bag, MD/MM |  |  |  | 20357 | 2 | PC | 3617
2
3
4
5
6
7 | [10 empty] | Date/Signature of Engineer
8 | [10 empty] | 2013-11-08 | Jesse Jones
9 | [10 empty] | Date/Signature of OIC
10 | [10 empty] | 2013-11-08 | S Christner
11 | [10 empty] | Date/Signature of Supervisor
12 | [10 empty] | 2013-11-08 | R Modesty
Comments: | [10 empty] | Material Doc.: | 4900812403
No
Yes
No
Commissioning
Yes
Technical Improvement (TQI)
Retrofit (WTI/WTA)(TI/TO)
Breakdown
Maintenance
Warranty Job
Other: