## General Information
Order | Order Type | Bas. start date | Description | Description | Functional loc. | System status | User status | Entered by | Changed by | WBS element | WBS ord. header | Actual release | Basic fin. date
402063675 | ZPM2 | 2015-07-26 | GAM-2106 TEMP MEASUREMENT FAIL | G97 / 90 / 4 - Patton | WF-US-0PA-1121-Y2-A-004 | CLSD PCNF NMAT SETC | COMP | OSB_RFC01 | IDUCAY01 |  |  | 2015-07-27 | 2015-07-26
402063666 | ZPM2 | 2015-07-27 |  | G97 / 90 / 4 - Patton | WF-US-0PA-1121-Y2-A-004 | CLSD DLFL NMAT SETC | COMP | OSB_RFC01 | LRAWLE01 |  |  | 2015-07-27 | 2015-07-27
402063668 | ZPM2 | 2015-07-27 |  | G97 / 90 / 9 - Patton | WF-US-0PA-1121-Y2-A-008 | CLSD DLFL NMAT SETC | COMP | OSB_RFC01 | LRAWLE01 |  |  | 2015-07-27 | 2015-07-27
402063678 | ZPM2 | 2015-07-27 | GAM-CHANGE PITCH RAM HALFMOONS | G97 / 90 / 9 - Patton | WF-US-0PA-1121-Y2-A-008 | CLSD PCNF GMPS NMAT SETC | COMP | OSB_RFC01 | IDUCAY01 |  |  | 2015-07-27 | 2015-07-27
402064108 | ZPM2 | 2015-07-27 | GAM-205 low HYD oil | G97 / 90 / 6 - Patton | WF-US-0PA-1121-Y2-A-006 | CLSD PCNF GMPS NMAT SETC | COMP | OSB_RFC01 | IDUCAY01 |  |  | 2015-07-27 | 2015-07-27
402065786 | ZPM2 | 2015-07-28 | GAM-205 LOW HG OIL | G97 / 90 / 6 - Patton | WF-US-0PA-1121-Y2-A-006 | CLSD PCNF GMPS NMAT SETC | COMP | OSB_RFC01 | IDUCAY01 |  |  | 2015-07-29 | 2015-07-28
402065835 | ZPM2 | 2015-07-28 | GAM-212 LEAK IN HUB | G97 / 90 / 6 - Patton | WF-US-0PA-1121-Y2-A-006 | CLSD PCNF NMAT SETC | COMP | OSB_RFC01 | IDUCAY01 |  |  | 2015-07-29 | 2015-07-28

## Hours (Labor)
Order | Turbine Number | Start Date | Sta. Hour | End Date | End Hour | Work type | Pers. No. | Personnel Name | Name 1 | Subcontract | WO Description | Order Type | User Status | Windfarm code | Windfarm Description | Functional Location | Planning plant | Stop Cause | Stop Cause Code | Stopped Work | Stopped Work Code | Windf. | WO Description | Work | Work Code | Work description | Work Hours | Total Hours | Posting date
402063675 | G97 / 90 / 4 - Patton | 2015-07-26 | 10:06 | 2015-07-26 | 11:08 | Op regular hours | 350800 | Michael Van Williams | GAMESA WIND USA | 500504 | GAM-2106 TEMP MEASUREMENT FAIL | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-004 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | Local reset | 1.03 | 62 | 42212
402063675 | G97 / 90 / 4 - Patton | 2015-07-26 | 10:06 | 2015-07-26 | 11:08 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | GAMESA WIND USA | 500504 | GAM-2106 TEMP MEASUREMENT FAIL | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-004 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | Local reset | 1.03 | 62 | 42212
402063678 | G97 / 90 / 9 - Patton | 2015-07-27 | 8:00 | 2015-07-27 | 12:25 | Op regular hours | 2002542 | DAVID SAMUEL PRICE | GAMESA WIND USA | 500504 | GAM-CHANGE PITCH RAM HALFMOONS | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-008 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | changed pitch ram half moons on all blades | 4.42 | 265 | 42212
402063678 | G97 / 90 / 9 - Patton | 2015-07-27 | 8:00 | 2015-07-27 | 12:23 | Op regular hours | 2000541 | Robert Anthony Cook | GAMESA WIND USA | 500504 | GAM-CHANGE PITCH RAM HALFMOONS | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-008 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | changed pitch ram half moons on all blades | 4.38 | 263 | 42212
402063678 | G97 / 90 / 9 - Patton | 2015-07-27 | 8:00 | 2015-07-27 | 12:25 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | GAMESA WIND USA | 500504 | GAM-CHANGE PITCH RAM HALFMOONS | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-008 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | changed pitch ram half moons on all blades | 4.42 | 265 | 42212
402064108 | G97 / 90 / 6 - Patton | 2015-07-27 | 15:25 | 2015-07-27 | 16:20 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | GAMESA WIND USA | 500504 | GAM-205 low HYD oil | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | added hyd oil | 0.92 | 55 | 42214
402064108 | G97 / 90 / 6 - Patton | 2015-07-27 | 15:25 | 2015-07-27 | 16:20 | Op regular hours | 2000507 | Nathan Paul Palko | GAMESA WIND USA | 500504 | GAM-205 low HYD oil | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | added hyd oil | 0.92 | 55 | 42214
402065786 | G97 / 90 / 6 - Patton | 2015-07-28 | 3:45 | 2015-07-28 | 11:50 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | GAMESA WIND USA | 500504 | GAM-205 LOW HG OIL | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 8.08 | 485 | 42214
402065786 | G97 / 90 / 6 - Patton | 2015-07-28 | 3:45 | 2015-07-28 | 11:50 | Op regular hours | 2000541 | Robert Anthony Cook | GAMESA WIND USA | 500504 | GAM-205 LOW HG OIL | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 |  | 8.08 | 485 | 42214
402065835 | G97 / 90 / 6 - Patton | 2015-07-28 | 15:05 | 2015-07-28 | 18:45 | Op regular hours | 2001212 | KEVIN BARCLAY JOHNSON | GAMESA WIND USA | 500504 | GAM-212 LEAK IN HUB | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | HUB LIGHT CAME LOOSE | 3.67 | 220 | 42214
402065835 | G97 / 90 / 6 - Patton | 2015-07-28 | 15:05 | 2015-07-28 | 18:45 | Op regular hours | 2000541 | Robert Anthony Cook | GAMESA WIND USA | 500504 | GAM-212 LEAK IN HUB | ZPM2 | Complete | 1121 | Patton | WF-US-0PA-1121-Y2-A-006 | 1320 |  | 0 |  | 0 | US/1121 | WO Maintenance Small corrective |  | 0 | HUB LIGHT CAME LOOSE | 3.67 | 220 | 42214

## Stop Times
Order | Plant | FunctLocDescrip. | Descriptn | WO Description | Windfarm | Start Date | Time | End date | Stop time | Total Stop | Order Type | Functional Location | External c | Descrip. o | Ext. Cause | Internal c | Descrip. o | Int. Cause | UserStatus | Line Hours | Employee | Production | Wind T. Av | WindT. hou | Disconnec. | Con. Hour | Name | System Status | Remarks | Total Fibe | Plant sect | Total Fibe | Hours for | Bas. Start | Basic fin. | Dis. Date | Connection | Total Stop
402063675 | 1320 | G97 / 90 / 4 - Patton | Patton | GAM-2106 TEMP MEASUREMENT FAIL | WF-US-0PA-1121 | 2015-07-26 | 21:51:00 | 2015-07-26 | 22:44:00 | 0:53:00 | ZPM2 | WF-US-0PA-1121-Y2-A-004 | 0 |  |  | 0 |  |  | COMP | 22581 | 0 | 18988488.00 KWH |  | 21917 | 00:00:00 | 00:00:00 |  | CLSD PCNF NMAT SETC | Local reset |  |  | 0 | 0.88 | 2015-07-26 | 2015-07-26 |  |  | 0.88
402063678 | 1320 | G97 / 90 / 9 - Patton | Patton | GAM-CHANGE PITCH RAM HALFMOONS | WF-US-0PA-1121 | 2015-07-27 | 08:01:00 | 2015-07-27 | 12:23:00 | 4:22:00 | ZPM2 | WF-US-0PA-1121-Y2-A-008 | 0 |  |  | 0 |  |  | COMP | 22786 | 0 | 16002230.00 KWH |  | 22348 | 00:00:00 | 00:00:00 |  | CLSD PCNF GMPS NMAT SETC | changed pitch ram half moons on all blades |  |  | 0 | 4.37 | 2015-07-27 | 2015-07-27 |  |  | 4.37
402064108 | 1320 | G97 / 90 / 6 - Patton | Patton | GAM-205 low HYD oil | WF-US-0PA-1121 | 2015-07-27 | 15:18:00 | 2015-07-27 | 16:17:00 | 0:59:00 | ZPM2 | WF-US-0PA-1121-Y2-A-006 | 0 |  |  | 0 |  |  | COMP | 22559 | 0 | 18773772.00 KWH |  | 21887 | 00:00:00 | 00:00:00 |  | CLSD PCNF GMPS NMAT SETC | added hyd oil |  |  | 0 | 0.98 | 2015-07-27 | 2015-07-27 |  |  | 0.98
402065786 | 1320 | G97 / 90 / 6 - Patton | Patton | GAM-205 LOW HG OIL | WF-US-0PA-1121 | 2015-07-28 | 03:45:00 | 2015-07-28 | 11:50:00 | 8:05:00 | ZPM2 | WF-US-0PA-1121-Y2-A-006 | 0 |  |  | 0 |  |  | COMP | 22541 | 0 | 19321734.00 KWH |  | 22299 | 00:00:00 | 00:00:00 |  | CLSD PCNF GMPS NMAT SETC |  |  |  | 0 | 8.08 | 2015-07-28 | 2015-07-28 |  |  | 8.08
402065835 | 1320 | G97 / 90 / 6 - Patton | Patton | GAM-212 LEAK IN HUB | WF-US-0PA-1121 | 2015-07-28 | 15:05:00 | 2015-07-28 | 18:45:00 | 3:40:00 | ZPM2 | WF-US-0PA-1121-Y2-A-006 | 0 |  |  | 0 |  |  | COMP | 22559 | 0 | 19328126.00 KWH |  | 22319 | 00:00:00 | 00:00:00 |  | CLSD PCNF NMAT SETC | HUB LIGHT CAME LOOSE |  |  | 0 | 3.67 | 2015-07-28 | 2015-07-28 |  |  | 3.67

## Consumption
Order | Plnt | SLoc | Material | Material Description | MvT | Quantity in UnE | Amount in LC | Pstng Date
402064108 | 1320 | 1121 | GP013211 | F. A. GENERIC HYDRAULIC GROUP FLUIDS | 965 | -20 | -37.86 | 2015-07-29
402063678 | 1320 | 1121 | GP021965 | 100-115-40 FRICTION BEARING | 965 | -6 | -296.12 | 2015-07-27
402063678 | 1320 | 1121 | GP022073 | G87GF CYLINDER HOLDER (MACHINING) | 965 | -6 | -580.93 | 2015-07-27
402065786 | 1320 | 1121 | GP043460 | ACCU. 24.5L PREFILL PRESS. 73 BAR. (CE-A | 965 | -1 | -856.37 | 2015-07-29